|  |  |  |  |
| --- | --- | --- | --- |
| **Key Activities Charlotte St over next 3-month period** | **Duration** | **Start** | **Finish** |
| Temporary Works - weathering system/scaffolding to resi(ladder beams to rear above office roof level) - roof level / crash barrier deck level 3/No 65 / propping system - flat 1/ No 65 | 12 days | 29/09/2016 | 14/10/2016 |
| Demolition existing Office Area/ envelope/structure/floor slabs | 30 days | 17/10/2016 | 28/11/2016 |
| Demolition of Residential area |  |  |  |
| Soft Strip | 15 days | 08/11/2016 | 28/11/2016 |
| Remove roof /windows | 15 days | 14/11/2016 | 02/12/2016 |
| Weathering to part walls - felt and batten | 6 days | 28/11/2016 | 05/12/2016 |
| Office |  |  |  |
| Civils | 20 days | 11/11/2016 | 08/12/2016 |
| Bulk Dig Basement - P1 -P4 P5-P6 | 15 days | 18/11/2016 | 08/12/2016 |
| House Deck Piling system priority lift pits and stair cores | 25 days | 02/12/2016 | 17/01/2017 |
| Note: Piling alternatives are currently being investigated. |  |  |  |